## Jeffrey
Date | What did you do yesterday? | What will you do today? | Are there any impediments in your way?
2019-03-03 | Try to contact all new memvbers | Try to contact all new memvbers | Try to contact all new memvbers
2019-03-04 | Try to contact all new memvbers | Try to contact all new memvbers | Try to contact all new memvbers
2019-03-05 | Contact PO for gathering all new member | set up meeting on 7th of March, 2019 | lack of communication between group member
2019-03-06 | intoduce the project with to all new member | Remind for meeting, and confirm attendance, meet supervisor | /
2019-03-07 | Research technicial resource for group members | Hold the meeting, setup environement for all team members | Ethan suddenly busy, can't attend the meeting
2019-03-08 | Arrange individual meeting with Ethan, because we didn't attend the meeting | Meet client with product owner | Client wants to restructure the whole project
2019-03-09 | annoce the current situation with all members, and meeting with PO about what should we do | Find tutorial resources for all group member, so once PO had finished user stories, everyone can start their work smoothly | All members are IS in our group, low programming skills
2019-03-10 | Find tutorial resources for all members | set up meeting on 14th of March, 2019 | Client didn't reply our email
2019-03-11 | Research about AWS and heroku | Choose one to deploy application | no
2019-03-12 | Deployed web server and database to aws | Research about authentication | What is jWT? Don’t understand
2019-03-13 | Research about JWT, dicuss with PO about the current situtation, trying to force PO send more email to client and give user stories | implement JWT and passport js | Client finally reply use, but we have meeting on 14th meeting, need to arrange all documents
2019-03-14
2019-03-15
2019-03-16
2019-03-17
2019-03-18
2019-03-19
2019-03-20
2019-03-21
2019-03-22
2019-03-23